## Register
HSE Hazard & Risk Register
| Project Name: | Pipeline Maintenance Risk Assessment | [12 empty] | Cat | Catastrophic
| Scope: | Pipeline Maintenance | [5 empty] | Insert the Risk Number from the RAM under People, Assets, Environment, Reputation | [6 empty] | Maj | Major
[15 empty] | Mod | Moderate
[15 empty] | Min | Minor
[15 empty] | Ins | Insignificant
| Hazard Ref | Description of Hazard | Description of scenario | Consequences |  |  |  | Potential Risk |  |  |  | Assessment/recommendation | Controls | Responsible person
[5 empty] | Overall Risk Rank | Impact | Likehood | People | Assets | Environment | Reputation
Phases
Phase 1 and 8 | Gravity - falling or things falling | Falling objects | Objects may fall around the working area while erecting and dismantling the scaffolding | Bruises, sprains, fractures, strains or at worst brain damage if severe impact on worker's head | 20 | 5 | C | 20 |  |  | 5 | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. | Use danger tags such as "Danger, Scaffolding Incomplete" or "Keep Out - Authorised Persons Only". Be careful when erecting or dismantling scaffolding, use mechanical hoist to move scaffolding components. Use PPE around working area to minimise risk (helmet, googles and safety boots) | Shift Supervisor/Senior Manager
Phase 1 and 8 | Gravity - falling or things falling | Workers falling at any height | Scaffold collapse due to incorrect matching of scaffolding components | Bruises, sprains, fractures, strains or long-term disability depending of the height of the scaffolding | 20 | 4 | D | 20 | 10 |  | 5 | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. | Obtain certification before working with scaffolding . Scaffold components must be matched correctly and securely tightened. Safety plan or manual must be followed. Use PPE around working area to minimise risk (helmet, googles and safety boots) Workers must use protective belt when using scaffolding. | Shift Supervisor/Senior Manager
Phase 1 and 8 | Electrical - contact or arcing | Electrical shock from broken electric lines | Setting up scaffolding near powerlines or electric lines | Pain, numbness, temporary amnesia, respiratory arrest, seizure, or even death | 20 | 5 | C | 20 | 5 |  | 5 | Unacceptable risk: Review process/equipment and properly implement controls before using the equipment. Senior management must review and only approve task when controls are implemented. Operations do not continue until risk is reduced. | Use warning signs and danger tags such as "Danger" or "Keep Out - Authorised Persons Only". Use PPE around working area to minimise risk (helmet, googles, safety boots and electrical resistant gloves) All power equipment must be tagged, tested and grounded and yearly maintenance and check must be done. | Shift Supervisor/Senior Manager
Phase 1 and 8 | Pressure - air, spring, liquid | Long hose or cable connections | Leaks or broken hose on pipeline that is used for compressor | Permanent eye injury if compressed air was directed to eyes and hearing disability | 20 | 3 | E | 20 | 5 |  | 2 | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. | Do maintenance and physical inspection. Use warning signs and danger tags such as "Danger- Equipment in Use" or "Keep Out - Authorised Persons Only". Use PPE around working area to minimise risk (helmet, googles, safety boots) | Senior Manager
Phase 1 and 8 | Electrical - contact or arcing | Faulty equipment | Short circuit from electrical power line of compressor and heater | Pain, numbness, temporary amnesia, respiratory arrest, seizure, or even death | 20 | 4 | D | 20 | 10 |  | 5 | Unacceptable risk: Review process/equipment and properly implement controls before using the equipment. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. | Do maintenance and physical inspection. Use warning signs and danger tags such as "Danger- Equipment in Use" or "Keep Out - Authorised Persons Only". Use PPE around working area to minimise risk (helmet, googles, safety boots and electrical resistant gloves) | Shift Supervisor/Senior Manager
Phase 2 and 7 | Noise - level and duration | High noise environment | Use of oxy-cutter and other equipment contacting steel pipe creating high noise levels | Industrial hearing loss in longer term with potential future financial liability | 20 | 4 | D | 20 | 5 |  | 2 | Unacceptable Risk: Immediately check records of health implications and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. | Use decibel reader to determine noise level <110db wear ear plugs >110db wear ear plug and ear muff protection | Worker/Contractor Supervisor Senior Manager (protocols)
Phase 2 and 7 | Mechanical - moving vehicles or parts | Automatic actuator failure | Automatic valve actuator fails and pipe does not isolate from top revisor causing loss of containment | Flooding of work area causing potential minor injury (no workers in tunnel at this time), asset damage or loss, major project delay | 20 | 3 | E | 10 | 20 | 15 | 10 | Unacceptable Risk: Immediately check records of risk and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. | Valve to undergo quarterly mechanical/control assessment Replaced if corroded and unresponsive | Worker/Contractor Supervisor Senior Manager (protocols)
Phase 2 and 7 | Technology –less than adequate design, beyond design use, cyber hacking | Undetectable dust/water/etc | Faulty or miscalibrated alarms do not identify water leaks from valve, or light levels of dust/contaminants in atmosphere | Minor to fatal personal injury with potential financial liability, and major operational delay | 15 | 5 | B | 10 | 5 | 15 | 3 | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. | Monitoring undergone annually mechanical/control assessment Testing regularly prior and during project Manual confirmation prior to work | Worker/Contractor Supervisor Senior Manager (protocols)
Phase 2 and 7 | Chemical - toxic, flammable/explosive | Inhalation /toxic chemical exposure | Fumes (Fe, C, epoxy) discharged from oxy-cutting of steel pipe are inhaled or in contact with persons | Asphyxiation, long term health implications (lung disease), future financial liability and possible reputational damage (i.e. such as that seen with asbestosis and black lung) | 20 | 4 | D | 20 |  | 10 | 3 | Unacceptable Risk: Immediately check records of health implications and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. | Wear welding and safety helmet with respirator Monitor dust and contaminants with alarmed personal measuring devices Use PPE around working area to minimise risk (helmet, googles, safety boots, full body protective bodysuit, gloves and mask should be worn) | Worker/Contractor Supervisor Senior Manager (protocols)
Phase 2 and 7 | Electrical - contact or arcing | Contact or arching of welder | Welder (which works by arcing with steel pipework) causes electrical shock or burn to worker due to misuse | Major to fatal personal injury with potential financial liability. | 15 | 5 | A | 15 | 5 |  |  | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. | Use PPE around working area to minimise risk (Wear welding and safety helmet with respirator, thermal resistant gloves and protective clothing) Used by approved and trained workers Equipment to undergo annual mechanical/electrical assessment. Yearly maintenance and check of these electrical equipment must be done. | Worker/Contractor Supervisor Senior Manager (protocols)
Phase 3 and 7 | Gravity - falling or things falling | Rolling equipment | Unsecured scaffolding or epoxy sprayer gains momentum and rolls down tunnel. | Major or fatal personal injury to workers, damage to downhill equipment | 15 | 5 | A | 15 | 5 | 5 | 5 | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. | Lockable scaffolding and epoxy sprayer wheels Check of all wheels to ensure they are locked Install wheel chocks Use PPE around working area to minimise risk (helmet, googles, safety boots) | Senior Manager
Phase 3 and 8 | Emergent – new/unexpected human-technology interactions/disruptions | Lack of access to exits in evacuation scenario | Workers obstructed from exiting tunnel due to scaffolding, lack of lighting or objects on ground | Workers could be trapped inside tunnel in emergency situation, leading to suffocation and/or death | 20 | 5 | C | 20 |  |  | 10 | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. Action must be taken to minimise the possibility of workers being trapped inside tunnel. | Battery powered lights and signs along tunnel and at exit Cords and hoses must be kept to side of tunnel and middle of tunnel must be kept clear at all times. Scaffolding must have clear, unobstructed, central exit. | Senior Manager
Phase 4 and 5 | Gravity - falling or things falling | Working at heights | Worker or equipment falls while sanding or applying new epoxy due to no barriers on scaffold | Moderate injury i.e. bruises, sprains, fractures or can be worse i.e. permanent disability; equipment breakages | 20 | 4 | D | 20 | 5 |  | 5 | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. Action must be taken to minimise the possibility of workers being trapped inside tunnel. | Use PPE around working area to minimise risk (helmet and goggles) Safety harnesses or barriers should be considered, placement of soft platform on the ground surrounding the scaffold, ensuring all workers follow the safety rules to minimise risk Obtain work height permit before any work is commenced | Shift Supervisor/ Senior Management
Phase 4 and 5 | Chemical - toxic, flammable/explosive | Toxic chemical exposure | Exposure to toxic epoxy dust (in low and high quantities) | Short Term: current or prolonged exposure can cause skin and eye irritation, allergic skin reactions, respiratory tract (nose, throat, and lungs) irritation, or breathing difficulties Long Term: bronchitis, cancer | 20 | 3 | E | 20 |  |  | 5 | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. Action must be taken to minimise the possibility of workers being trapped inside tunnel. | Use PPE around working area to minimise risk (full body protective bodysuit, gloves and mask should be worn) Ensure all work and storage areas are uncluttered and clean Provide a changing area for workers to change out of work clothes Ensure there is a regular clean-up schedules during each shift Consider applying a fixed or portable ventilation system to keep the chemical vapours from building up in the work area Workers should be trained for correct handling of epoxy Dust alarms must be installed to monitor epoxy particulates | Shift Supervisor/ Senior Management
Phase 4 and 5 | Chemical - toxic, flammable/explosive | Toxic chemical exposure | Epoxy dusts accumulating to high concentration in surrounding confined work area | Explosions, serious injury and/or fatalities | 25 | 5 | D | 25 |  |  |  | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. Bow-tie analysis is recommended. Review existing controls associated with high concentrations of epoxy in the air. | Onsite inspection required before commencement of work. Dust ignition protected vacuums may be considered as all electrical components can be enclosed to prevent source of ignition. Can provide dust alarms to monitor epoxy particulates and notify workers at the lower explosive limit (LEL) | Senior engineer/ Senior Management
Phase 4 and 5 |  |  |  | Damage to equipment, financial loss | 20 | 4 | D |  | 20
Phase 4 and 5 |  |  |  | Environmental contamination affecting humans, as well as flora and fauna growth | 20 | 4 | D |  |  | 20
Phase 4 and 5 |  |  |  | Business interruption, fines and penalties, lawsuits | 20 | 4 | D |  |  |  | 20
Phase 4 and 5 | Thermal - hot/cold surfaces | Heat Sources and dust | Accumulation of dust on hot surface of floodlight or heater, causing ignition of dust | Major or fatal personal injury to workers, major damage to equipment and tunnel | 20 | 5 | C | 20 | 10 |  | 3 | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. Action must be taken to minimise the possibility of workers being trapped inside tunnel. | Minimise the number of people in the tunnel at all times. Routine checks and cleaning of lights and heaters. Equip scaffolding with automatic fire suppression equipment. Use PPE around working area to minimise risk (helmet, googles, safety boots, full body protective bodysuit, gloves and mask should be worn) | Senior Manager
Phase 4 and 5 | Chemical - toxic, flammable/explosive | Heat build-up in mixing tank | Large volume of epoxy left to cure (harden) in mixing tank for more than 20 minutes due to chemical reaction of epoxy being exothermic/heat generating | Generation of heat that can melt mixing tank, burn skin | 20 | 5 | C | 20 | 10 |  | 10 | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. Action must be taken to minimise the possibility of workers being trapped inside tunnel. | Include a temperature sensor with alarm in the tank for monitoring and to alert other workers on site Possible cooling system installed for mixing tank Provide a flame arrestor to trap ignition of flame in mixing tank Pressure alarm in mixing tank to notify workers Install fire extinguisher at epoxy storage system Use PPE around working area to minimise risk (full body protective bodysuit, gloves and mask should be worn) | Shift Supervisor/ Senior Management
Phase 4 and 5 |  |  |  | Ignition of surrounding combustible materials and cause explosions, emissions to atmosphere | 20 | 5 | C |  | 10 | 20 | 10
Phase 4 and 5 | Chemical - toxic, flammable/explosive | Toxic chemical exposure | Exposure to toxic solvent through leaks or spillage | Current or prolonged exposure can cause respiratory, eye and skin irritation, organ and nervous system damage or cancer | 20 | 4 | D | 20 | 5 | 5 | 5 | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented to prevent fire or explosions Operations do not continue until risk is reduced. Action must be taken to minimise the possibility of workers being trapped inside tunnel. Mitigate impact by knowing the lower explosive limit (LEL) of the solvent. | Provide an eyewash and shower station outside the confined area Install lower explosive limit (LEL) alarms in the confined work area Install a ventilation system Use PPE around working area to minimise risk (full body protective bodysuit, gloves and mask should be worn) | Shift Supervisor/ Manager
Phase 4 and 5 | Chemical - toxic, flammable/explosive | Toxic chemical exposure | Loss of flammable solvent whilst flushing out the mixing tank, hoses and spraying system | Fire, storage explosion and severe worker injuries or fatalities if in contact with an ignition source (i.e. heaters, static electricity) and oxygen in the air | 25 | 5 | D | 25 | 10 | 10 | 2 | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. Action must be taken to minimise the possibility of workers being trapped inside tunnel. | Provide sealed transportation of flammable solvent to the sprayer system Ensure sprayer system valves and pipework are regularly monitored Ensure regular supplies are provided and stocked (i.e. brooms, mops, spill kits, chemical absorbers, waste bins) Use PPE around working area to minimise risk (full body protective bodysuit, gloves and mask should be worn) | Shift Supervisor/ Manager
Phase 4 and 5 | Chemical - toxic, flammable/explosive | Abrasive sandblasting | Exposure to large quantities of airborne silica dust (from sand) | Bodily injuries, incurable silicosis (lung disease), damage to equipment | 20 | 4 | D | 20 |  |  | 5 | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. Action must be taken to minimise the possibility of workers being trapped inside tunnel. Review existing controls and procedures associated with preventing worker exposure to silica dust | Use PPE around working area to minimise risk (hearing protection safety boots, respiratory mask for head, neck and shoulders; eye and face protection, gloves) Provide training to abrasive blasters Support personnel on blasting health and safety hazards: regular air test and monitoring devices on machines and operators, exhaust ventilation, use safety signs or barriers to isolate blasting areas Consider a safer method i.e. water blasting, consider the use of a less hazardous blasting media Decontaminating equipment on a regular basis Re-entry testing for silica dust | Shift Supervisor/ Senior Management
Phase 4 and 5 | Chemical - toxic, flammable/explosive | Silica dust clouds forming from sandblasting | Worker vision impairment within the confined space leading to accidental trips or falls | Severe physical injuries to workers, damage to equipment | 20 | 3 | E | 20 | 10 |  |  | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. | High speed exhaust ventilation Schedule sandblasting operations during favourable weather conditions and when fewer workers are present Sandblasting tests conducted before work commences to roughly determine degree of vision impairment from dust Use PPE around working area to minimise risk (full body protective bodysuit, gloves and mask should be worn) | Shift Supervisor/ Manager
Phase 2-7 | Chemical - toxic, flammable/explosive | Low oxygen content | Failure of air quality controls in ventilation, alarms and monitors leading to excessive heat, accumulation of epoxy dust and silica particles, toxic fumes | Impaired judgement, fatigue, unconsciousness, acute health problems, death | 20 | 5 | C | 20 | 10 | 10 |  | Unacceptable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Operations do not continue until risk is reduced. Recommendations for control measures for air quality and heat (i.e. average air velocity 0.3-2m/s at all times, amount of air 1.5m3/min per worker and 4m3/min per kW rated diesel power, wet bulb temperature > 27oC | Tag and test, as well as maintenance and calibration of all air alarms, monitors and ventilation Check ventilation for dead spots, low speed air areas, areas of dust concentration, recirculation of dusty air, inspection points were blockages may occur Ventilation must be located as close as possible to contamination area | Worker, contractors, senior management
Phase 1 and 8 | Body Mechanics - lifting, position etc | Manual handling i.e. moving or lifting heavy load or equipment | Repetitive or sustained force when handling heavy equipment, high or sudden force, awkward posture | Muscular aches and pains or worst, long-term musculoskeletal disorder | 10 | 3 | D | 10 | 5 |  | 2 | Tolerable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Demonstration of ALARP Band 2 is required. | Implement workshops or training for correct lifting techniques when doing manual handling/ heavy lifting. Worker can use mechanical aids to potentially eliminate long term musculoskeletal disorder caused by manual heavy lifting. | Shift Supervisor/Senior Manager
Phase 1 and 8 | Body Mechanics - lifting, position etc | Lifting and manuvering heavy items/equipment | Lifting equipment around circular pipe to cut and mauver with heavy steel pipe cut out section (~2.5 tonne) | Muscle strain or tendon injuries with potential financial liability | 10 | 3 | D | 10 | 5 |  | 2 | Tolerable Risk: Immediately check records of injury and identify the cause of risk to eliminate/minimize potential hazard. Senior management must review and only approve task only when controls are implemented. Demonstration of ALARP Band 2 is required. | Weight restrictions on what can be lifted by 1 person manually e.g. 25kg Scaffolding and platforms for equipment required at height | Worker/Contractor Supervisor Senior Manager (protocols)
Phase 1 and 8 | Gravity - falling or things falling | Hazardous step | Workers might slip and fall when climbing the ladder | Bruises, sprains, fractures, strains or long-term disability depending of the height of the ladder | 10 | 4 | C | 10 |  |  | 3 | Tolerable Risk: Regular checks from any damage and maintenance to ensure safety. Inform the senior management or engineers for any damages on the ladder. Senior management must review and only approve task only when controls are implemented. Demonstration of ALARP Band 2 is required. | Proper training of workers is needed to set up ladder correctly. Ladder must be left in proper condition after use. If any damage was observed, report immediately to senior management. Workers must use protective belt when using ladder. Use PPE around working area to minimise risk (helmet, googles and safety boots) | Shift Supervisor/Senior Manager
Phase 2 and 7 | Thermal - hot/cold surfaces | Thermal burns | Worker is burned by oxy-cutter when making tunnel opening | Significant personal injury to workers from burns causing loss of work time and company health incident | 10 | 2 | E | 5 | 10 |  | 5 | Tolerable Risk: Regular checks from any damage to ensure safety. Senior management must review and only approve task only when controls are implemented. Demonstration of ALARP Band 2 is required. | Thermal resistant gloves and clothing. Use PPE around working area to minimise risk (safety glasses, face shield) Obeyed policy regarding oxy-cutter use Used by approved and trained workers Equipment undergone annual mechanical/electrical assessment | Worker/Contractor Supervisor Senior Manager (protocols) Maintenance
Phase 2 and 7 | Gravity - falling or things falling | Working over open cavity | Worker falls into tunnel whilst making tunnel opening | Significant personal injury from fall from height causing loss of work time and company health incident, also increases risk to persons recovering the injured | 10 | 2 | E | 10 | 5 |  | 3 | Tolerable Risk: Regular checks from any damage to ensure safety. Senior management must review and only approve task only when controls are implemented. Demonstration of ALARP Band 2 is required. | Opening remains tethered to a source (pipe, crane, stand etc.) at all times Cutting workspace/positions restricted to zones where fall potential is minimised due to centre of gravity management Work from ladders faced in front not by kneeling/standing on pipework Use PPE around working area to minimise risk (helmet, googles and safety boots) | Worker/Contractor Supervisor Senior Manager (protocols)
Phase 2 and 7 | Thermal - hot/cold surfaces | Fire / engulfment | Oxy-cutter contacts fuel source such as wooden ladder, epoxy dust, or oil/fuel | Minor personal injury with potential financial liability, asset damage or loss, major operational delay | 10 | 3 | C | 10 | 5 | 5 | 2 | Tolerable Risk: Regular checks from any damage to ensure safety. Senior management must review and only approve task only when controls are implemented. Demonstration of ALARP Band 2 is required. | Fire emergency plan (practiced by workers) Safety equipment available at work site i.e. extinguishers Removal of potential fuel sources instructed in Take 5 (wood, oil, dust) Monitor dust and contaminants with alarmed measuring devices Use PPE around working area to minimise risk (helmet, googles, safety boots, heat resistant gloves and mask should be worn) | Worker/Contractor Supervisor Senior Manager (protocols)
Phase 2 and 7 | Mechanical - moving vehicles or parts | Failure of crane during use | Workers poorly attach cut out 2.2 tonne pipe section, as crane that lifts section it falls | Minor personal injury with potential financial liability, asset damage or loss, major project delay | 10 | 3 | C | 10 | 5 | 5 | 2 | Tolerable Risk: Regular checks from any damage to ensure safety. Senior management must review and only approve task only when controls are implemented. Demonstration of ALARP Band 2 is required. | Equipment undergone annual mechanical/electrical assessment Items secured to crane verified safe by other workers prior to lift | Worker/Contractor Supervisor Senior Manager (protocols)
Phase 2 and 7 | Body Mechanics - lifting, position etc | Manually shutting valve | If valve contains a secondary manual spot along with automatic actuator it must be manually closed. This mechanism may be tight or rusty. | Muscle strain or tendon injuries with potential financial liability | 10 | 2 | E | 10 | 5 |  |  | Tolerable Risk: Regular checks from any health implications to ensure safety. Senior management must review and only approve task only when controls are implemented. Demonstration of ALARP Band 2 is required. | Task completed by two persons Not proceeded if working ineffectively | Worker/Contractor Supervisor Senior Manager (protocols)
Phase 2 and 7 | Thermal - hot/cold surfaces | Thermal burns using welder and Fire/engulfment | Pipe opening resealed by welding where molten steel particles can be projected contacting worker or ignition source | Minor to fatal personal injury with potential financial liability, asset damage or loss | 10 | 3 | C | 10 | 5 |  |  | Tolerable Risk: Regular checks from any injuries to ensure safety. Senior management must review and only approve task only when controls are implemented. Demonstration of ALARP Band 2 is required. | Wear welding and safety helmet with respirator 'Fire emergency plan (practiced by workers) Safety equipment available at work site i.e. extinguishers Removal of potential fuel sources instructed in Take 5 (wood, oil, dust) Thermal resistant gloves and clothing. Used by approved and trained workers Equipment undergone annual mechanical/electrical assessment | Worker/Contractor Supervisor Senior Manager (protocols)
Phase 2 and 7 | Mechanical - moving vehicles or parts | Automatic actuator failure | Automatic valve actuator fails during recommissioning preventing pipe use | Loss of work time, project delay | 10 | 2 | E |  | 10 |  |  | Tolerable Risk: Regular checks required to ensure safety. Senior management must review and only approve task only when controls are implemented. Demonstration of ALARP Band 2 is required. | Equipment undergone quarterly mechanical/control assessment | Worker/Contractor Supervisor Senior Manager (protocols)
Phase 2 and 7 | Mechanical - moving vehicles or parts | Welding on resealed entrance failure | During recommissioning pressure on internal pipe increases causing weaker welded zones to fail, potentially leading to full pipe failure | Asset damage or loss, major operational delay | 10 | 2 | E |  | 10 |  |  | Tolerable Risk: Regular checks required. Senior management must review and only approve task only when controls are implemented. Demonstration of ALARP Band 2 is required. | Work completed and checked by qualified welder and supervisor Water added gradually to monitor weld behaviour as flow pressure builds | Worker/Contractor Supervisor Senior Manager (protocols)
Phase 3 and 6 | Thermal - hot/cold surfaces | Heat Sources | Worker is burned by hot surface of floodlight or heater | Personal injury to workers from burns | 10 | 2 | E | 10 |  |  | 2 | Tolerable Risk: Regular checks required. Senior management must review and only approve task only when controls are implemented. ALARP Band 1 – Action as a high priority to reduce risk. Mitigate likelihood by setting up site to minimise worker contact with hot surfaces. | Position lights and heaters away from common work areas (eg on outside of scaffolding) Paint lights and heaters bright colours and have signs warning workers about hot surfaces around scaffolding Use PPE around working area to minimise risk (helmet, googles, safety boots and body protective bodysuit) | Senior Manager
Phase 4 and 5 | Chemical - toxic, flammable/explosive | Toxic chemical exposure | Loss of containment of the chemicals due to spillage from carrying the chemicals to the sprayer system or pouring it into the hoppers | Current or prolonged exposure can cause skin and eye irritation, allergic skin reactions, respiratory tract (nose, throat, and lungs) irritation, or breathing difficulties due to toxic vapours | 10 | 3 | C | 10 | 5 | 5 |  | Tolerable Risk: Regular checks required. Senior management must review and only approve task only when controls are implemented. ALARP Band 1 – Action as a high priority to reduce risk. Mitigate likelihood by setting up site to minimise worker contact with hot surfaces. | Use PPE around working area to minimise risk (full body protective bodysuit, gloves and mask should be worn) Provide sealed transportation of chemicals to the sprayer system Ensure regular supplies are provided and stocked (i.e. brooms, mops, spill kits, chemical absorbers, waste bins), | Shift Supervisor/ Manager
Phase 4 and 5 | Pressure - air, spring, liquid | High pressure and speed of compressed air | Incorrect use, sudden release or failure of air sandblasting at high pressure | Minor to severe injuries to workers and others in the area | 10 | 2 | E | 10 | 5 |  |  | Tolerable Risk: Regular checks required. Senior management must review and only approve task only when controls are implemented. ALARP Band 1 – Action as a high priority to reduce risk. Mitigate likelihood by setting up site to minimise worker contact with hot surfaces. | Have minimal amount of workers at a time during sandblasting Use PPE around working area to minimise risk (full body protective bodysuit, gloves and mask should be worn) | Shift Supervisor/ Manager
Phase 1 and 8 | Mechanical - moving vehicles or parts | Transporting scaffolding (sharp edge) | Accidentally swing the sharp edge of scaffolding component to any co-worker | Cuts/puncturing | 5 | 2 | B | 5 |  |  |  | Tolerable Risk: Review process/equipment and properly implement controls before using the equipment. Senior management must review and only approve task only when controls are implemented. Demonstration of ALARP Band 2 is required. Can be minimised by using PPE at work. | Obtain certification before working with scaffolding . Safety plan or manual must be followed. Use PPE around working area to minimise risk (helmet, googles, safety boots) | Shift Supervisor/Senior Manager
Phase 1 and 8 | Human capability – slips, lapses, errors | Long hose or cable connections | Slips, trips and falls | Bruises, sprains, fractures and strains | 5 | 2 | D | 5 | 2 |  |  | Tolerable Risk: Review existing controls and any suggested controls. Senior management must review and only approve task only when controls are implemented. Demonstration of ALARP Band 2 is required. | Make sure no hose or cable connections on the floor when working to avoid slips and trips. Properly secure the cable connections using a stand to clear working space | Shift Supervisor/Senior Manager
Phase 4 and 5 | Noise - level and duration | Spray system and sand blasting in operation | Excessive noise and vibrations for extended periods of time | Noise-induced hearing loss to persons onsite, worsened communication onsite | 5 | 1 | E | 5 |  |  |  | Tolerable Risk: Regular checks from any damage and maintenance to ensure safety. Inform the senior management or engineers for any damages on the ladder. Senior management must review and only approve task only when controls are implemented. Demonstration of ALARP Band 1 is required. | Use PPE around working area to minimise risk (use of hearing protection (headset) by all workers onsite) | Shift Supervisor/ Manager
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## RAM
Risk Ranking Matrix | [5 empty] | Likelihood
Impact | [5 empty] | Rare | Unlikely | Moderate | Likely | Almost Certain
Impact | OH&S | Asset damage | Environment | Reputation / Legal |  | Not expected to occur (but has occurred in industry) | Might occur once in entity's life | Could occur every 5-10 years | Could occur every 1-5 years | could occur monthly, weekly or daily
[6 empty] | A | B | C | D | E
Catastrophic | Fatalities | > $50 m | Serious LT effect | Widespread serious adverse impact | 5 | 15 | 15 | 20 | 25 | 50
Major | Permanent, serious disability | $10m - $50 m | Serious Med to LT effect | Wider spread moderate impact | 4 | 5 | 10 | 10 | 20 | 25
Moderate | Moderate irreversible impairment | $1m - $10m | Moderate ST to Med effect | Localised(Qld) moderate | 3 | 3 | 5 | 10 | 10 | 20
Minor | Objective but recoverable impairment | $100k - $1m | Minor Short term effect | Localised(Qld) Minor | 2 | 2 | 5 | 5 | 5 | 10
Insignificant | First aid / minor | < $100 k | Low level / no lasting effect | No impact | 1 | 1 | 2 | 3 | 5 | 5
Risk Rating | 15 - 50 | High | Unacceptable Risk |  | Unacceptable – Operations do not to continue until risk is reduced.
| 10 - 14 | Significant | Tolerable Risk (only if risk reduction is impracticable or it's cost is grossly disproportionate to improvement gained) |  | ALARP Band 1 – Action as a high priority to reduce risk. Assign senior manager responsible to action, monitor and review. If interim measures installed monitor closely and continuously.
| 4 - 9 | Medium |  |  | ALARP Band 2 – Action to reduce risk where possible. Assign manager responsible to continuously monitor and review
| 1 - 3 | Low | Broadly Acceptable |  | Generally Acceptable - Manage with regular monitoring and review.

## HAZID Codes (hidden)
Section 1: External & Environmental Hazards
Code | Category | Hazard/Event Guideword | Scenario
1.01 | Natural and Environmental Hazards | Climate Extremes | Temperature, waves, wind, dust, flooding, sandstorms, ice, blizzards
1.02 |  | Lightning
1.03 |  | Earthquakes
1.04 |  | Erosion | Ground slide, coastal, riverine
1.05 |  | Subsidence | Ground structure, foundations, reservoir depletion
2.01 | Created (Man-made) Hazards | Security Hazards | Internal and external security threats
2.02 |  | Terrorist Activity | Riots, civil disturbance, strikes, military action, political unrest
3.01 | Effect of the Facility on the Surroundings | Geographical - Infrastructure | Plant location, plant layout, pipeline routing, area minimisation
3.02 |  | Proximity to Population
3.03 |  | Adjacent Land Use | Crop burning, airfields, accommodation camps
3.04 |  | Proximity to Transport Corridors | Shipping lanes, air routes, roads, etc
3.05 |  | Environmental Issues | Previous land use, vulnerable fauna and flora, visual impact
3.06 |  | Social Issues | Local population, local attitude, social/cultural areas of significance
4.01 | Infrastructure | Normal Communications | Road links, air links, water links
4.02 |  | Communications for Contingency planning
4.03 |  | Supply Support | Consumables/spares holding
5.01 | Environmental Damage | Continuous Plant Discharges to Air | Flares, vents, fugitive emissions, energy efficiency
5.02 |  | Continuous Plant Discharges to Water | Target/legislative requirements, drainage facilities, oil/water separation
5.03 |  | Continuous Plant Discharges to Soil | Drainage, chemical storage
5.04 |  | Emergency/upset Discharges | Flares, vents, drainage
5.05 |  | Contaminated Ground | Previous use or events
5.06 |  | Facility Impact | Area minimisation, pipeline routing, environmental impact assessment
5.07 |  | Waste Disposal Options
5.08 |  | Timing of Construction | Seasons, periods of environmental significance
Section 2: Facility Hazards
6.01 | Control Methods/ Philosophy | Manning/operations Philosophy | Effect on design, effect on locality (Manned, unmanned, visited)
6.02 |  | Operations Concept | 1 train, x-trains, simplification
6.03 |  | Maintenance Philosophy | Plant/train/equipment item, heavy lifting, access, override, bypass, commonality of equipment, transport
6.04 |  | Control Philosophy | Appropriate technology, (DCS/local panels)
6.05 |  | Manning Levels | Accommodation, travel, support requirements. Consistency with operations and maintenance, etc philosophies
6.06 |  | Emergency Response | Isolation, ESD philosophy, blowdown, flaring requirements
6.07 |  | Concurrent Operations | Production, maintenance requirements
6.08 |  | Start-up Shutdown | Modular or plant wide
7.01 | Fire and Explosion Hazards | Stored Flammables | Improper storage, operator error (release), defect, impact, fire (mitigation measures include: substitute non flammable, minimise and separate inventory)
7.02 |  | Sources of Ignition | Electricity, flares, sparks, hot surfaces (mitigation measures include: identify, remove, separate)
7.03 |  | Equipment Layout | Confinement, escalation following release of explosive or flammable fluid (operator error, defect, impact process control failure, corrosion), module layout/proximity, orientation of equipment, predominant wind direction (mitigation measures include: reduce degree of confinement, spacing based on consequence assessment, escalation barriers)
7.04 |  | Fire Protection and Response | Active/passive insulation, fire/gas detection, blowdown/relief system philosophy, firefighting facilities
7.05 |  | Operator Protection | Means of escape, PPE, communications, emergency response, plant evacuation
8.01 | Process Hazards | Inventory | Excess hazardous material (mitigation measures include: minimise hazardous inventory, alternate processes and utility systems)
8.02 |  | Release of inventory | Excessive process stress, impact (penetration by foreign object), process control failure, structural failure, erosion or corrosion (mitigation measures include: recognise and minimise process hazards during design, inherently safe plant, containment and recovery measures)
8.03 |  | Over Pressure | Offsite sources, process blockage, thermal expansion, connection of process to utility systems, chemical reaction
8.04 |  | Over/under Temperature | Atmospheric conditions, blowdown, fire, hot surfaces, chemical reaction
8.05 |  | Excess/zero Level | Overfill storage tanks, loss of function in separation vessels, blowby to downstream vessels
8.06 |  | Wrong Composition/Phase | Offsite contamination, failure of separation process, build-up of wrong phase (sand, hydrates, etc), toxic substances
9.01 | Utility Systems | Firewater Systems
9.02 |  | Fuel Gas
9.03 |  | Heating / Cooling Medium
9.04 |  | Diesel Fuel
9.05 |  | Power Supply
9.06 |  | Steam
9.07 |  | Drains
9.08 |  | Inert Gas
9.09 |  | Waste Storage and Treatment
9.1 |  | Chemical/fuel Storage
9.11 |  | Potable Water
9.12 |  | Sewerage
10.01 | Maintenance Hazards | Access Requirements
10.02 |  | Override Necessity
10.03 |  | Bypasses Required
10.04 |  | Commonality of Equipment
10.05 |  | Heavy Lifting Requirements
10.06 |  | Transport
11.01 | Construction/ Existing Facilities | Tie-ins (shutdown requirements)
11.02 |  | Concurrent Operations
11.03 |  | Reuse of Material
11.04 |  | Common Equipment Capacity
11.05 |  | Interface - Shutdown/blowdown/
11.06 |  | ESD
11.07 |  | Skid Dimensions (weight handling/equipment (congestion)
11.08 |  | Soil Contamination (existing facilities)
11.09 |  | Mobilisation/ demobilisation
Section 3: Health Hazards
12.01 | Health Hazards | Disease Hazards | Endemic diseases, infection, malarial mosquitoes, hygiene - personal and/or catering, contaminated water or foodstuff, social, e.g. AIDS, VD, etc stagnant water, poor living conditions
12.02 |  | Asphyxiation hazards | Asphyxiating atmospheres, failure to use appropriate PPE, vessel entry, working in confined spaces, smoke, exhaust
12.03 |  | Carcinogenic | Chemicals in use
12.04 |  | Toxic | Hazardous atmosphere, asphyxiating atmosphere, chemicals in use
12.05 |  | Physical | Noise, radiation (ionising, e.g. radioactive scale or non-ionising, e.g. flares, UV, sunlight), ergonomics
12.06 |  | Mental | Shift patterns
12.07 |  | Working Hazards | Diving, working in water, working at heights, hazardous equipment, hazardous surfaces, electricity
12.08 |  | Transport | Excessive journeys, extreme weather, quality of roads (mitigation measures include: effective journey management)
Section 4: Project Implementation Issues
13.01 | Contracting Strategy | Prevailing influence | Stability and contractual conditions, contractor selection constraints
13.02 |  | Legislation | Governmental contracting requirements
13.03 |  | External Standards | Additional engineering and construction standards
13.04 |  | External Environmental Constraints | Governmental environmental requirements
14.01 | Hazards Recognition and Management | Hazard Studies | HAZOP, SAFOP, QRA, FIREPRAN, PHR, EA, HRA, etc
14.02 |  | HSE Case
14.03 |  | Hazards and Effects Register
14.04 |  | Project Controls | Quality assurance (change control, interdepartmental involvement and interfaces)
15.01 | Contingency Planning | Geographical Infrastructure | Plant location, plant layout
15.02 |  | Recovery Measures | Medical support, firefighting support, spill leak/clean-up support, security/military support, evacuation
16.01 | Competency | Level of Indigenous Training | Quality of local workforce and contractors
16.02 |  | Training Requirements
16.03 |  | Level of Technology

## Hazard ref
Hazards
Gravity - falling or things falling
Electrical - contact or arcing
Mechanical - moving vehicles or parts
Chemical - toxic, flammible/explosive
Pressure - air, spring, liquid
Noise - level and duration
Thermal - hot/cold surfaces
Radiant - light, radiation
Body Mechanics - lifting, position etc
Human capability – slips, lapses, errors
Technology –less than adequate design, beyond design use, cyber hacking
Environmental conditions – weather/climate
Social/political/community – activism, terrorism, unauthorised access
Biological – animal-borne, human-borne, vegetable-borne
Psychological – harassment, abuse, stress, fatigue
Emergent – new/unexpected human-technology interactions/disruptions
Project management constraints and limitations